RETIREMENTTRACK

Task 10 – MVP Backlog, Implementation Plan & Estimate

# 1. Purpose & Executive Summary

This document converts the Discovery decisions into a practical implementation plan for the first production-ready RetirementTrack release. The objective is to preserve the product’s distinctive recurring-engagement model while keeping the first build focused, secure, supportable and commercially testable.

# 2. What the First Build Must Prove

| MVP outcome | What success looks like |
| --- | --- |
| Firm-ready SaaS foundation | A firm can be configured, branded and securely isolated from every other firm. |
| Simple client onboarding | A client/household can be invited, activate access with MFA, complete minimum profile information and understand household sharing. |
| Personalized retirement journey | The client sees a small number of relevant priorities, visible progress, milestones and educational items rather than a generic task list. |
| Recurring engagement | Planning Updates, selected assessments, reminders, milestones and educational content create reasons to return before and during retirement. |
| Low routine advisor workload | Client accomplishments, outstanding items and true advisor exceptions are separate; routine engagement does not automatically create advisor work. |
| Professional-judgment boundary | The system identifies issues, considerations and opportunities but does not provide individualized financial, investment, tax or legal recommendations. |
| Pilot-operable platform | RetirementTrack owns production accounts; deployment, monitoring, backups, recovery, access and support procedures are ready for pilot use. |

# 3. Prioritization Model

| Priority | Meaning | Treatment |
| --- | --- | --- |
| P0 – Foundation / Launch Required | Security, tenancy, identity, data integrity, deployment and core operating controls. | Must be completed before production pilot. |
| P1 – Core MVP Value | Features that demonstrate RetirementTrack’s differentiated client/advisor engagement model. | Must be in the first usable MVP. |
| P2 – Pilot Important / Simplified | Needed for credible pilot operation but intentionally narrow/configured. | Build a simple version; avoid generalized engines. |
| P3 – Post-MVP / Future | Valuable capabilities that are not necessary to validate the first build. | Preserve extension points; do not build now. |

# 4. Dependency Map & Critical Path

| Dependency | Why it matters | Schedule effect if late |
| --- | --- | --- |
| Azure/Git/Clerk/Temporal accounts under RetirementTrack control | Required for secure environments, authentication and durable workflow setup. | Blocks foundation and production-readiness work. |
| Tenant/household/domain model | All client, advisor, assessment, content and lifecycle data depends on these boundaries. | Rework risk across most features. |
| Assessment/scoring and Planning Update rules | Needed to implement results, comparisons and advisor exceptions. | Blocks core recurring workflow completion. |
| Education content/taxonomy | Needed to validate browse and contextual surfacing experience. | Can use seed content temporarily; pilot quality affected. |
| Benchmark source/method approval | Licensing, cohort method and calculation must be credible. | Benchmark can be feature-flagged/deferred without blocking core MVP. |
| Communication sender/provider readiness | Needed for invitations/reminders and deliverability testing. | Blocks end-to-end reminder/UAT scenarios. |
| Legal/privacy/retention language | Needed for production notices, household sharing and final lifecycle policy. | Does not block early coding but can block launch. |

# 5. Recommended Team Structure

| Role | Recommended involvement | Primary responsibility |
| --- | --- | --- |
| Full-Stack Engineer | Full-time | Frontend and backend development, architecture implementation, core features, integrations, testing, code reviews, and deployment support. |
| Full-Stack Engineer | Full-time | Frontend and backend development, feature implementation, integrations, testing, bug fixes, and ongoing development support. |
| Independent Reviewer | Phase 6 | Pre-Production Security & Architecture - Full Implementation Verification |

# 6. Implementation Backlog

The current implementation backlog totals 980 hours. Developer-level unit/feature testing is included in the relevant implementation items, with formal system validation, independent review and production launch represented separately.

| # | Implementation Workstream | Hours |
| --- | --- | --- |
| 1 | Foundation, Repo, IaC & Environments | 36 |
| 2 | Clerk Pro Identity & MFA | 46 |
| 3 | Tenancy, Firm, Roles & Advisor Assignment | 56 |
| 4 | Household, Client & Privacy Model | 46 |
| 5 | White-Label & Firm Configuration | 20 |
| 6 | Onboarding & Invitations | 34 |
| 7 | Client Dashboard, Personalization, Journey & Progress Meter | 72 |
| 8 | Planning Updates | 58 |
| 9 | Assessments, Scoring & History | 60 |
| 10 | Engagement, Outstanding Items & Advisor Exceptions | 46 |
| 11 | Advisor Dashboard & Exception Handling | 50 |
| 12 | Education Library & Contextual Surfacing | 52 |
| 13 | Milestones, Reminders, Communications & Temporal Cloud | 74 |
| 14 | Benchmarking MVP | 30 |
| 15 | Firm / Platform Administration Basics | 30 |
| 16 | Audit, Security, Data Lifecycle & Portability | 56 |
| 17 | Monitoring & Operational Readiness | 56 |
| 18 | Stage, UAT, Accessibility, Security & Performance | 66 |
| 19 | Independent Pre-Production Security & Architecture Reviewer | 46 |
| 20 | Production Launch & Handoff | 46 |
|  | Total | 980 |